## Sheet1
Comprehensive Timeline: FOCUS PDCA | 2014-07-01 | 2014-08-01 | 2014-09-01 | 2014-10-01 | 2014-11-01 | 2014-12-01 | 2015-01-01 | 2015-02-01 | 2015-03-01 | 2015-04-01 | 2015-05-01 | 2015-06-01 | 2015-07-01 | 2015-08-01
| 7/25/14 – Met and discussed Unit based needs and identified topic for project with LZ | 8/1/14 – Began clinical and evidence based practice research for OR Preceptorship | 9/12/14 – Began writing AIP OR Preceptor Survey questions | 10/1/14 - Distributed OR Preceptorship Survey Monkey to AIP II OR Staff | 11/17/14 - Met with LZ to review Preceptorship survey results & completed FOCUS PDCA | 12/11/14 - Met with LZ to complete Level of Evidence for OR Preceptorship article reviews | 1/26/15 - Present AIP OR Preceptor Survey Results & FOCUS PDCA PowerPoint at staff meeting |  | 3/25/15 - Facilitated OR Specific Basic Preceptor Course to 6 AIP OR staff | 4/17/15 - Reviewed FOCUS PDCA – began working on 4 week post-course survey | 5/1/15 – Closed OR Specific Basic Preceptor Course post survey and began analyzing results | · 6/8/15 – Connected with KS and SS to review plan for upcoming Preceptor courses and possibility of extending invitations to Sterile Processing Department (SPD) for preceptor training | 7/6/15 – Completed analysis and organization of OR Specific Basic Preceptor Course post-course SM and PR survey results (5.28.15 course)
|  |  | 9/15/14 – Sent rough draft AIP OR Preceptor Survey to KM for review | 10/21/14 – Met with LZ to discuss Survey progress and started FOCUS PDCA | 11/25/14 – Began development of FOCUS PDCA and Preceptorship Survey Results PowerPoint and AIP OR Preceptorship PowerPoint | 12/11/14 – Completed OR Preceptorship Literature Review |  |  |  | 4/24/15 – Distributed 4 week post-course survey to OR Specific Basic Preceptor Course learners (3/25/15 session, Survey Monkey (SM)) to complete | 5/8/15 – Completed analysis and organization of OR Specific Basic Preceptor Course post- course survey results | 6/23/15 – Reviewed FOCUS PDCA and distributed 4 week post-course survey to OR Specific Basic Preceptor Course learners (5/28/15 session) to complete | 7/14/15 – Met with LZ to review second course surveys data and discuss future review as act to determine the next steps (FOCUS PDCA) with offering of OR Specific Basic Preceptor Course post-transition to Lippincott education platform
|  |  | 9/23/14 – Revised AIP OR Preceptor Survey | 10/31/14 – Closed OR Preceptorship survey to review, analyze & categorize results |  | 12/20/14 – Complete OR Preceptorship Literature Review Condensed Notes with Levels of Evidence |  |  |  | 4/29/15 – Scheduled second OR Specific Basic Preceptor Course with Joanne Gadol and booked classroom | 5/8/15 – Distributed invite to OR staff for OR Specific Basic Preceptor Couse on 5/28/15 | 6/29/15 – Obtained post-course OR Specific Basic Preceptor Course Professional Resources Preceptor Program Survey data from BH
|  |  | 9/25/14 – Met with KM to build AIP OR Preceptor Survey on Survey Monkey |  |  | 12/29/14 – Met with LZ to review FOCUS PDCA PowerPoint presentation and organize data to present to OR staff |  |  |  |  | 5/8/15 – Closed invite, distributed Preceptor Welcome email to enrolled staff for OR Specific Basic Preceptor Course | 6/30/15 – Closed OR Specific Basic Preceptor Course post-course survey and began analyzing results
5/12/15 – Completed analysis and organization of OR Specific Basic Preceptor Course post course Preceptor Program Professional Resources survey results
5/28/15 – Facilitated second OR Specific Basic Preceptor Course to 6 AIP OR staff and 1 AOP staff member
5/29/15 Met with LZ to review portfolio/FOCUS PDCA R/T preceptorship course and reflect/review OR Specific Preceptor Course