## Sheet1
Condensed Timeline: OR Specific Basic Preceptor Course | 2014-07-01 | 2014-08-01 | 2014-09-01 | 2014-10-01 | 2014-11-01 | 2014-12-01 | 2015-01-01 | 2015-02-01 | 2015-03-01 | 2015-04-01 | 2015-05-01 | 2015-06-01 | 2015-07-01 | 2015-08-01
| 7/25/14 – Met and discussed Unit based needs and identified topic for project with LZ | 8/1/14 – Began clinical and evidence based practice research for OR Preceptorship | 9/3/14 – Met and discussed project idea with KM | 10/1/14 - Distributed OR Preceptorship Survey Monkey to AIP II OR Staff | 11/17/14 - Met with LZ to review survey results & completed FOCUS PDCA | 12/11/14 - Met with LZ to complete Level of Evidence for article reviews | 1/15/15 – Met with Bebe Hoff (BH) to discuss Basic Preceptor Course content/development and plan revising Preceptor Policy | 2/11/15 - Distributed OR specific facilitated discussion scenarios with rationale for review to KM, MB, LZ and BH | 3/2/15 – Met with MB to review prep for OR Specific Basic Preceptor Course | 4/14/15 - Obtained post-course OR Specific Basic Preceptor Course Professional Resources Preceptor Program Survey data from BH | 5/1/15 – Closed OR Specific Basic Preceptor Course post survey and began analyzing results | 6/8/15 - Connected with KS and SS to reivew plan for upcoming Preceptor courses and possibility of extending invitations to Sterile Processing Department (SPD) for preceptor training | 7/6/15 – Completed analysis and organization of OR Specific Basic Preceptor Course post-course SM and PR survey results (5.28.15 course)
|  |  | 9/12/14 – Began writing AIP OR Preceptor Survey questions | 10/21/14 – Met with LZ to discuss Survey progress and started FOCUS PDCA | 11/25/14 – Met with KM and LZ to propose AIP OR Preceptor Manual/education course | 12/11/14- Completed OR Preceptorship Literature Review | 1/26/15 - Present AIP OR Preceptor Survey Results & FOCUS PDCA PowerPoint at staff meeting | 2/20/15- Scheduled OR Specific Basic Preceptor Course with Joanne Gadol and scheduled classroom | 3/2/15 - Met with LZ to review project outline, preceptor course items and ORPC items | 4/17/15 - Reviewed FOCUS PDCA – began working on 4 week post-course survey | 5/8/15 – Completed analysis and organization of OR Specific Basic Preceptor Course post- course survey results | 6/23/15 – Distributed 4 week post-course survey to OR Specific Basic Preceptor Course learners (5/28/15 session) to complete | 7/14/15 - Met with LZ to reivew second course survey data and discuss future review and offering of OR Specific Basic Preceptor course post transition to Lippencott education platform.
|  |  | 9/15/14 – Sent rough draft AIP OR Preceptor Survey to KM for review | 10/31/14 – Closed OR Preceptorship survey to review, analyze & categorize results | 11/25/14 - Began development of FOCUS PDCA and Preceptorship Survey Results PowerPoint and AIP OR Preceptorship PowerPoint | 12/20/14 - Completed OR Preceptorship Literature Reivew Condensed Notes with Levels of Evidence |  | 2/20/15- Distributed invites to OR Specific Preceptor Course to all AIP OR Staff | 3/16/15 - Reivewed OR specific facilitated discussion scenarios and rationale with ORPC members | 4/17/15 - Distributed Professional Resources Preceptor Program post-course data to SS, SS, JG, KM & LZ from BH to advocate for second OR Specific Basic Preceptor Course to be scheduled | 5/8/15 – Distributed invite to OR staff for OR Specific Basic Preceptor Couse on 5/28/15 | 6/29/15 – Obtained post-course OR Specific Basic Preceptor Course Professional Resources Preceptor Program Survey data from BH
|  |  | 9/23/14 – Revised AIP OR Preceptor Survey |  |  | 12/29/14 – Met with LZ to review PowerPoint presentations and organize data to present to OR staff |  | 2/20/15- Closed invite, distributed Preceptor Welcome email to enrolled staff for OR Specific Basic Preceptor Course | 3/19/15 - Obtained approval from ORPC members to utilize OR specific facilitated discussion scenarios as primary tool in upcoming OR Specific Basic Preceptor Course | 4/21/15 – Connected with June Fouse (Ambulatory Services-Clinical Nurse Educator) regarding OR Preceptor Program and training (OR Specific Basic Preceptor Course and resources) | 5/8/15 – Closed invite, distributed Preceptor Welcome email to enrolled staff for OR Specific Basic Preceptor Course | 6/30/15 – Closed OR Specific Basic Preceptor Course post-course survey and began analyzing results
|  |  | 9/25/14 – Met with KM to build AIP OR Preceptor Survey on Survey Monkey |  |  | 12/30/14 – Met with LZ and Monica Brock (MB) to discuss Scenarios/evaluation tools etc. |  | 2/25/15- Contacted KM for distribution of online modules for OR Specific Preceptor Course | 3/25/15 - Facilitated OR Specific Basic Preceptor Course to 6 AIP OR staff | 4/24/15 – Distributed 4 week post-course survey to OR Specific Basic Preceptor Course learners (3/25/15 session, Survey Monkey (SM)) to complete | 5/12/15 – Completed analysis and organization of OR Specific Basic Preceptor Course post course Preceptor Program Professional Resources survey results
[8 empty] | 2/27/15 - Contacted BH to advocate for online modules release for OR Techs to complete |  | 4/29/15 – Scheduled second OR Specific Basic Preceptor Course with Joanne Gadol and booked classroom | 5/28/15 – Facilitated second OR Specific Basic Preceptor Course to 6 AIP OR staff and 1 AOP staff member
[8 empty] | 2/27/15 - Met with LZ to complete final review of OR specific facilitated discussion questions, AIP OR Preceptorship PowerPoint and development of Preceptor Manual /Reference Book |  |  | 5/29/15 Met with LZ to review portfolio and reflect/review OR Specific Preceptor Course