## Sheet1
Condensed Timeline: Teaching Standard Intraoperative EPIC Documentation Tool | 2014-07-01 | 2014-08-01 | 2014-09-01 | 2014-10-01 | 2014-11-01 | 2014-12-01 | 2015-01-01 | 2015-02-01 | 2015-03-01 | 2015-04-01 | 2015-05-01 | 2015-06-01 | 2015-07-01 | 2015-08-01
|  |  | 9/3/14 – Met and discussed project ideas with KM |  |  | 12/10/14 - Met with KM, Suzanne Sortman (SS), Kristi Schuessler (KS) on OR Charting Guidelines | 1/9/15 – Closed EPIC OR Charting Guidelines Survey and began analyzing results | 2/9/15 – Met with EPIC Charting Guideline team to start reviewing charting questions/concerns | 3/3/15 - Met with KS to review EPIC Intraop chart & divide sections for writing Guideline | 4/1/15 – Met with KS, began transcribing/formatting sections into Guideline Rough Draft #1 | 5/4/15 – Met with Teaching Standard Intraoperative EPIC Documentation stakeholders to review rough draft #3 | 6/15/15 - Obtained final e-vote for unanimous approval of Teaching Standard: Intraoperative EPIC Documentation tool | 7/1/15 - Met with KS to orgnaize plan for circulation of Teaching Standard: Intraoperative EPIC Documentation tool to include posting to Weebly education site, informative email and formal presentation at OR staff meeting | 8/14/15 - Completed PowerPoint presentation for formal education to OR staff of Teaching Standard: Intraoperative EPIC Documentation tool
[6 empty] | 12/10/14 - Began EPIC Charting Guidelines Survey development with KS | 1/15/15 - Completed AORN Recommended Practices review and summary of Pratices V-IX. | 2/18/15 – Met with EPIC Charting Guideline team to continue reviewing charting questions/concerns | 3/5/15 - Began reviewing and writing EPIC Guideline sections | 4/2/15 – Met with LZ discussed transitioning EPIC Charting Guideline format | 5/4/15 - Obtained reivew from Nursing Practice Guideline Committee, approved changes from Guideline to Teaching Standard tool. Removed agenda reservation to present for committee reivew. | 6/22/15 – Met with KS to review plan for formal presentation of Teaching Standard: Intraoperative EPIC Documentation Tool | 7/2/15 - Teaching Standard: Intraoperative EPIC Documentation tool posted to OR educational website uchor.weebly.com | 8/24/15 - Co-presentation with KS for formal education of Teaching Standard: Intraoperative EPIC Documentation tool at OR staff meeting
[6 empty] | 12/11/14 - Sent KM EPIC OR Charting Guidelines Survey rough draft | 1/20/15 - Completed EPIC Charting Guidelines Surveys analysis and comparision charts | 2/18/15 – Distributed EPIC Charting Guideline meeting minutes (2.18.15) | 3/12/15- Contacted Nursing Practice Guideline Committee to reserve upcoming agenda time to present the EPIC Intraopertive Charting Guideline for review | 4/14/15 – Distributed EPIC Charting Document Rough Draft #1 to task force team | 5/13/15 – Completed and distributed Teaching Standard Intraoperative EPIC Documentation Final draft and Table of Contents to KS, KM and LZ for final review | 6/22/15 – Contacted SS, SS and Gail King to place bid for OR staff meeting agenda time to formally present Teaching Standard: Intraoperative EPIC Documentation Tool | 7/6/15– Distributed informational email to entire OR staff acknowledging the Teaching Standard: Intraoperative EPIC Documentation Tool upload to the OR Weebly education site and formal education of tool will be presented in August 2015
[6 empty] | 12/12/14 - Finalized EPIC OR Charting Guidelines Survey and distributed to AIP OR Service Specialist and seasoned RN’s |  | 2/23/15- Met with EPIC Charting Guideline team to start reviewing charting questions/concerns | 3/15/15 - Contacted Transplant Service Specialist Peter Benson to review current pratices and anticipated changes related to Transplant Timeout documentation in EPIC and/or current use of paper forms | 4/20/15 – Met with KM and KS to review EPIC Charting Guideline Draft #1, discussed formatting, primary use of document/primary audience | 5/13/15 - Contacted RaeLynn Caudle to reivew TrackCore updates related to implant documentation in EPIC | 6/23/15 - Began PowerPoint presentation for formal education of Teaching Standard: Intraoperative EPIC Documentation tool
[6 empty] | 12/18/14 - Began literature review and AORN Recommended Practices Reivew |  | 2/23/15 - Distributed EPIC Charting Guideline meeting minutes (2.23.15) | 3/16/15 – Met with EPIC Charting Guideline team to continue reviewing charting questions/concerns | 4/22/15 – Distributed EPIC Charting Document Rough Draft #2 to KM, KS, LZ for review | 5/22/15 - Updated Implants section with TrackCore documentation requirements | 6/29/15 – Confirmed agenda reservation for formal presentation of Teaching Standard: Intraoperative EPIC Documentation Tool at OR staff Monday morning meeting 8/24/15
[9 empty] | 3/23/15 - Met with EPIC Charting Guideline team to continue reviewing charting questions/concerns | 4/27/15 – Met with KM and KS to review Teaching Standard Intraoperative EPIC Documentation (previously EPIC Charting Guideline) Draft #2 | 5/22/15 – Met with KS to review final draft, Table of Contents and creation of cover page
[9 empty] | 3/30/15 - Distributed EPIC Charting Guideline meeting minutes (3.16.15 & 3.23.15) | 4/27/15 - Contacted Nursing Practice Guideline Committee to update change from Guideline to Teaching Standard Tool. Provided Committee with EIPC Charting Document Rough Draft #2 for review and assess application to Committee for review | 5/26/15 – Completed cover page for Teaching Standard Intraoperative EPIC Documentation tool
[10 empty] | 4/30/15 – Distributed Teaching Standards Intraoperative EPIC documentation rough draft #3 to KS, KM, LZ | 5/27/15 – Distributed final draft of Teaching Standard Intraoperative EPIC Documentation to stakeholders for e-vote approval